## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Harhini.K.A | 2025-12-08 | Unused imports were not being detected correctly for certain Python files | Sprint 1 | Self | Logical | Improved AST traversal logic to correctly identify unused imports | 2025-12-09 | Closed | Issue resolved and validated with sample programs
2 | Harhini.K.A | 2025-12-09 | PEP8 style violations were not highlighted consistently in the output | Sprint 1 | Self | Standards | Integrated stricter PEP8 checks and improved formatting rules | 2025-12-11 | Closed | Style detection accuracy improved
3 | Harhini.K.A | 2026-01-15 | Syntax errors were not clearly explained to the user (only generic error shown) | Sprint 1 | Self | Logical | Enhanced error handling to provide detailed and user-friendly syntax error messages | 2026-01-17 | Closed | Error messages now clearly guide the use
4 | Harhini.K.A | 2026-01-17 | Code comparison feature was not highlighting differences properly for similar lines | Sprint 2 | Self | Logical | Improved comparison algorithm using line-by-line and token-based analysis | 2026-01-19 | Closed | Comparison accuracy improved significantly
5 | Harhini.K.A | 2026-01-21 | AI suggestions were sometimes irrelevant to the given code context | Sprint 2 | Self | Logical | Refined AI prompt handling and context extraction for better suggestions | 2026-01-25 | Closed | Suggestions are now more relevant and accurate

## Sheet2
Logical
User Interface
Maintainability
Standards
Others